## skyline architects
Client: Maharashtra National Law University, Mumbai
Project: Appointment of Project Management Consultant (PMC) for Development of Green Field Campus of MNLU Mumbai at Goregaon (West), Mumbai
Bidder: Skyline Architects
Sr. No. | Query No. | Query Description (Extracted from Annexure A) | Reply (Finalized for Submission)
1 | 1.1.2 – 1.3.5 | Statutory approvals and construction of the full campus including services and handing over to MNLU; clarification sought on role / duties of Architect and PMC. | MNLU has already appointed an Architectural Firm for design and development works. The PMC shall coordinate all related activities as mentioned in the relevant portion of the EOI.
3 | 5.5 | Request to reduce the average total annual consultancy-fee criterion (₹25 Crores for last 3 years) to ₹10 Crores. | Please follow the Revised EOI stipulation.

## Hill International
Client: Maharashtra National Law University, Mumbai
Project: Appointment of Project Management Consultant (PMC) for Development of Green Field Campus of MNLU Mumbai at Goregaon (West), Mumbai
Bidder: Hill International
Sr. No. | Clause Reference | Query Description | Reply
1 | Clause 5.3 – Minimum Eligibility Criteria | Request to allow high-rise residential buildings having similar complexities though purely residential complexes are not eligible. | The eligibility criteria shall remain as specified in the EOI.
2 | Clause 5.4 – Experience with Government | Request to allow ongoing building/infra projects with completed quantum > ₹100 Cr for Govt./PSU/public listed company with ₹500 Cr+ turnover. | Please follow the Revised EOI stipulation.
3 | Clause 7 – Fees Details | Request for monthly payment based on actual deployment of manpower (time-based contract). | Details will be available in the RFP document.
4 | Clause 7 – Fees Details | Request to accept Performance Bank Guarantee of 5% instead of retention from each bill. | Details will be available in the RFP document.
5 | General | Request to allow Joint Venture (maximum 2 firms). | Please follow the Revised EOI stipulation.
6 | General | Request to provide project building configuration and envisaged completion timeline. | Details of the master plan of the proposed campus are available on the homepage of MNLU Mumbai website under the head 'About University' at erp.mnlumumbai.edu.in. The project is expected to be completed within the next five years.

## Mukesh & Associates
Client: Maharashtra National Law University, Mumbai
Project: Appointment of Project Management Consultant (PMC) for Development of Green Field Campus of MNLU Mumbai at Goregaon (West), Mumbai
Bidder: Mukesh & Associates consultants & engineers
Sr. No. | EOI Clause No. & Page | Bidder’s Query / Clarification Sought | Remarks / Reply
1 | Clause 1 — Page 4 of 16 | The bidder has requested confirmation whether the mentioned 3,00,000 sq.m refers to the total land area or the built-up area of the proposed building. | It refers to the Proposed Built-Up Area (BUA) as per the planning and requirement.
2 | Clause 1.1 — Scope of PMC, Page 4 of 16 | The bidder has sought clarification on whether the Architectural Firm will handle the design works and whether the PMC’s role is limited to administrative coordination and management. | Confirmed. The Architectural Firm will undertake the design works. The PMC’s role will be limited to administration, coordination, supervision, and project management as per the EOI scope.
3 | Clause 9.7 & Clause 11.2 — Page 12 of 16 | The bidder has sought clarification regarding the mode of submission of the EOI, as Clause 9.7 specifies submission in sealed hard copy, while Clause 11.2 mentions submission by email to the Registrar. The bidder requests confirmation whether (i) only hard copy, (ii) only soft copy, or (iii) both submissions are required. | EOI documents are to be submitted in hard copy on or before 21.11.2025 at the given address of Maharashtra National Law University, Mumbai. Additionally, a soft copy of the submission may be shared at the email ID mentioned in the EOI document.

## Masters Management India Pvt Lt
Sr. No. | Clause No. & Page | Bidder’s Query / Clarification Sought | Remarks / Reply (MNLU Mumbai)
1 | Pg 05, 7 | Kindly confirm that drawings, documents preparation, and submission for statutory approvals are not in PMC's scope. | Confirmed. Preparation and submission of drawings/documents for statutory approvals are in the scope of the appointed Architectural Firm. The PMC is required to coordinate among different stakeholders to ensure timely processing and approvals.
2 | Pg 05, A.4 | Kindly clarify the extent of ‘Design Verification’. We understand that core design will be handled by the Architect, while PMC will review/verify based on standard practices. | Confirmed.
3 | Pg 05, A.6 | Please confirm the agency responsible for providing the BOQ and Tender documents for PMC’s coordination and vetting. | Architect.
4 | Pg 05, A.1 | Please clarify if Pre-construction PMC team can be stationed at Powai office on a need basis / visiting mode. | Details available in EOI and RFP documents. MNLU may provide office space at its present campus during the pre-construction stage, subject to availability.
5 | Pg 05, C.2 | Kindly confirm our understanding regarding assisting MNLU Mumbai in providing relevant project documents for arbitration/legal matters. | Project is scheduled to be completed within 5 years.
6 | Pg 06, 1.3 | Please clarify the project duration and timelines for (A) Pre-construction, (B) Construction, and (C) Defects Liability Period. | Details are being worked out and are not firmed as on date.
7 | New Point | Please clarify the envisaged procurement strategy for major packages and bought-out items. | Please follow the Revised EOI stipulation.
8 | Pg 10, 5.4 | Request you to allow ongoing projects for eligibility criteria. | Please follow the Revised EOI stipulation.
9 | Pg 10, 5.5 | Please consider reducing the average annual consultancy fee criteria to ₹13 Crores. | The average annual consultancy fee criterion shall be ₹20 Crore.
10 | Pg 12, 10 | Please clarify whether additional project certificates are required for the three similar projects under Section 05. | Please follow the Revised EOI stipulation.
11 | Pg 12, IV | Can projects with GRIHA/LEED ratings other than those mentioned be considered? | Please follow the Revised EOI stipulation.
12 | New Point | Plot area to be provided. | 35 acres of plot area with CRZ.
13 | New Point | Project value estimate to be provided. | Approx. ₹2000 Crore INR.
14 | New Point | Project site location/address. | Provided in Revised EOI documents.
15 | Clause 9.7 & 11.2 | The bidder has sought clarification on whether EOI submission is to be done in hard copy, soft copy, or both. | EOI documents are to be submitted in hard copy on or before 21.11.2025 at the MNLU Mumbai address. Additionally, a soft copy may be shared at the email ID mentioned in the EOI document.

## VBAPL
Client: Maharashtra National Law University, Mumbai
Project: Appointment of Project Management Consultant (PMC) for Development of Green Field Campus of MNLU Mumbai at Goregaon (West), Mumbai
Bidder: M/s Vivek Bhole Architects Pvt. Ltd.
Sr. No. | RFP Reference (Page No.) | Content of RFP Requiring Clarification | Points of Clarification Required | Remarks / Reply (MNLU Mumbai)
1 | Page No. 10, Point No. 5.5 – Average Annual Turnover | The average total annual consultancy fee received by the firm shall not be less than Rs. 25 Crores in the last 3 financial years ending on 31-03-2025. | Requesting you to kindly consider average annual turnover of 20 Crores in the last 3 financial years. | Please follow the Revised EOI stipulation.
2 | Page No. 10, Point – Work Experience | Purely residential complexes are not eligible. | Kindly consider completed/ongoing private residential projects. | Please follow the Revised EOI stipulation.
3 | Page No. 10, Point No. 5.4 – Experience with Government | Completed at least one assignment of minimum quantum of work with project cost of Rs. 100 Crore for Central/State Government, PSU, or autonomous body. | Please consider private projects also. | Please follow the Revised EOI stipulation.
4 | — | Kindly allow Joint Venture. | — | Joint Ventures are not allowed as per EOI condition.

## RITES Limited
Client: Maharashtra National Law University, Mumbai
Project: Appointment of Project Management Consultant (PMC) for Development of Green Field Campus of MNLU Mumbai at Goregaon (West), Mumbai
Bidder: RITES Limited
Sr. No. | Clause No. & Page | Query / Clarification Sought | Remarks / Reply (MNLU Mumbai)
1 | General | We understand that the scope of the EoI invited for Project Management Consultancy services does not include any Architectural or Design services. Kindly confirm our understanding. | Confirmed. The scope of work under the EoI for PMC services does not include Architectural or Design-related services. These activities shall be undertaken by the appointed Architectural Consultant.
2 | General (Page 8) | Kindly clarify whether Joint Venture (JV) participation is permitted in this tender. | Joint Ventures are not permitted as per the Revised EoI stipulations.
3 | Clause 5.3 of EoI | Request to include hospital buildings as part of the definition of similar works. | Standalone buildings shall not be considered under the definition of similar works.
4 | Clause 5.3 of EoI (Page 9) | Request to include a provision for enhancement of project cost at the rate of 7% per annum to bring the value to the current cost level, as per Ministry of Finance guidelines. | The matter was explained during the Pre-Bid Meeting. Bidders are requested to follow the Revised EoI stipulations.
5 | General | Kindly provide the following details: (1) Estimated project cost, and (2) Tentative number of phases planned for execution. | The estimated project cost is approximately ₹2000 Crore, and the project is proposed to be executed in a single phase.
6 | General | Kindly clarify whether MNLU intends to execute all future phases of the project with the PMC selected through this EoI/RFP or whether separate tenders will be invited for each package. | It is proposed to complete construction of all the facilities required for successful running of the University at the new campus in a single phase.

## TATAConsulting Engineers LTD
Client: Maharashtra National Law University, Mumbai
Project: Appointment of Project Management Consultant (PMC) for Development of Green Field Campus of MNLU Mumbai at Goregaon (West), Mumbai
Bidder: TATA Consulting Engineers Limited
Sr. No. | Clause No. & Page | Query / Clarification Sought | Remarks / Reply (MNLU Mumbai)
1 | General | Please brief us on the current status of the project, statutory clearances, and tentative start date of the project. | Explained during the Pre-Bid Meeting.
2 | General | Request to provide approximate construction cost of the project. | The estimated project cost is approximately ₹2000 Crore.
3 | General | Request to clarify tentative duration of the project as follows: • Pre-construction Period • Construction Period • Post-Construction Period • Defect Liability Period | Details are being worked out and are not firmed as on date. Tentatively, the total project duration is proposed to be 5 years including all stages.
4 | EOI Page No. 10, Clause 5.4 – Experience with Government | Request to revise the clause to: “The firms should have satisfactorily completed at least one assignment (either from above or separately) of minimum quantum of work with project cost of ₹500 Crore for Central/State Government, PSU, or an autonomous body.” | Please follow the Revised EOI stipulations.
5 | EOI Page No. 10, Clause 6 – Selection Process | Request to specify the marking system for the selection process. | Will be available in RFP documents.
6 | EOI Page No. 11, Clause 6 – Selection Process | Request to adopt QCBS (Quality-cum-Cost Basis Selection) method with 80% technical and 20% financial weightage. | Please follow the Revised EOI stipulations.

## Knight Frank (India) Pvt. Ltd.
Client: Maharashtra National Law University, Mumbai
Project: Appointment of Project Management Consultant (PMC) for Development of Green Field Campus of MNLU Mumbai at Goregaon (West), Mumbai
Bidder: Knight Frank (India) Pvt. Ltd.
Sr. No. | Clause | Query | Reply
1 | Clause 5.4 requires one assignment of Rs. 100 Cr | Can this be part of the assignments listed under the architect’s work? | Please follow the Revised EOI stipulation.
2 | Clause 1.3.2 & 1.3.9 (Staff Deployment) | Kindly share Table B / required staffing deployment details. | The required staffing deployment details will be provided in the RFP Document. Bidders are requested to refer to the RFP once published.
3 | Clause 5.7 (Affidavit Format) | Kindly confirm if a standard format will be provided. | Please follow the Revised EOI stipulation.
4 | Clause 8 (Pre-Bid Meeting) | Please confirm time, venue, and whether presentation was required. | Pre-bid meeting was conducted as scheduled on 18.10.2025. No presentations were required. The Minutes of Meeting and clarifications have been uploaded/shared as applicable.
5 | Clause 1.3 (PMC Duration) | Are we looking at deployment for 5 years for PMC team? | The PMC services are intended for the duration required for successful execution and completion of the project. Detailed timelines will be provided in the RFP.